## Matrix
Cause | Consequence | Likelihood (1-5) | Impact (1-5) | Score (likelihood * impact) | Risk mitigation | New likelihood (1-5) | New impact (1-5) | New score (new likelihood * new impact)
Approach requires too much time | Incomplete products | 4 | 4 | 16 | Creating a planning with time estimates; Weekly progress meetings | 2 | 2 | 4
Approach does not fit requirements | Unsatisfactory products | 3 | 3 | 9 | Weekly progress meetings | 1 | 2 | 2
Miscommunication on requirements | Unsatisfactory products | 2 | 4 | 8 | Doing a requirement interviews/brainstorm session with client and updating the requirements weekly through the use of agile development | 1 | 1 | 1
Illness | Stagnation of project | 2 | 3 | 6 | Creating a planning with small buffer for risks and communicating with supervisors on how to continue if necessary | 2 | 1 | 2
Project too big/complex | Inadequate solution | 3 | 3 | 9 | Updating the scope weekly through agile development | 1 | 2 | 2
Drone stops functioning properly | No proof of concept can be shown; stagnation of development | 3 | 3 | 9 | Purchasing replacement parts beforehand/Creating simulation | 2 | 1 | 2
No charged batteries left for the drone (drone can only be recharging via USB-cable attached to the drone) | Unable to test until recharged | 5 | 1 | 5 | Purchase a battery charging dock/Creating simulation | 1 | 1 | 1
Bug occurs | Solution does not function as desired; Stagnation of development | 4 | 2 | 8 | Create tests; Test regularly | 4 | 1 | 4
Loss of files/data | Loss of progression | 1 | 5 | 5 | Making use of version control | 1 | 1 | 1
|  |  |  | 75 |  |  |  | 19