## Matrix
Cause | Consequence | Likelihood (1-5) | Impact (1-5) | Score (likelihood * impact) | Risk mitigation | New likelihood (1-5) | New impact (1-5) | New score (new likelihood * new impact)
Approach requires too much time | Incomplete products | 4 | 4 | 16 | Weekly progress meetings and defining (time)limits | 2 | 4 | 8
Approach does not fit requirements | Unsatisfactory products | 3 | 3 | 9 | Weekly progress meetings | 1 | 2 | 2
Miscommunication on requirements | Unsatisfactory products | 1 | 3 | 3 | Weekly progress meetings and documentation | 1 | 1 | 1
Illness | Stagnation of project | 2 | 2 | 4 | Creating a planning with small buffer for risks and communicating with supervisors on how to continue | 2 | 1 | 2
Project too big/complex | Subpar solution | 3 | 3 | 9 | Properly defining a scope with supervisor | 2 | 2 | 4
Drone stops functioning properly | No proof of concept can be shown | 2 | 2 | 4 | Creating a simulation | 1 | 1 | 1
Loss of files/data | Loss of progression | 1 | 4 | 4 | Making use of a repository | 1 | 1 | 1
|  |  |  | 49 |  |  |  | 19